DANNHAUSER LOCAL MUNICIPALITY

DANNHAUSER LOCAL MUNICIPALITY

REVISED SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

2025/2026 FINANCIAL YEAR

Table of Contents

- Abbreviations

- Mayors Approval

- Municipal Manager’s Quality Assurance

- MFMA Legislative requirement

- 2024/2025 Service Delivery Budget Implementation Plan

- Technical Indicator Descriptions

- Abbreviations

DTI	Department of Trade and Industry

IA	Internal Auditor

IDP	Integrated Development Plan

INEP 	Integrated National Electrification Programme

MEC	Member of the Executive Council

MIG	Municipal Infrastructure Grant (Previously CMIP)

MM	Municipal Manager

PAC	Performance Audit Committee

PMS	Performance Management System

SDBIP	Service Delivery Budget and Implementation

- Mayor’s Approval

Municipal Finance Management Act, 56 of 2003 (MFMA), section 53 (1) states that the mayor of a municipality must—

(c) takes all reasonable steps to ensure-

(ii) that the municipality’s service delivery and budget implementation plan is approved by the mayor within 28 days after the approval of the budget; and

(iii) that the annual performance agreements as required in terms of section 57(1)(b) of the Municipal Systems Act for the municipal manager and all senior managers—

(aa) comply with this Act in order to promote sound financial management.

(bb) are linked to the measurable performance objectives approved with the budget and to the service delivery and budget implementation plan; and

(cc) are concluded in accordance with section 57(2) of the Municipal Systems Act. The Dannhauser Local Municipality’s 2025/26 annual budget was approved by Council on  during its Ordinary Council Meeting. Attached hereto, is the revised SDBIP for 2025/26 financial year that is to be adopted by the Council.

I, Cllr BA Radebe in my capacity as Mayor of Dannhauser Local Municipality, hereby confirm receipt of the Revised Service Delivery and Budget Implementation Plan (SDBIP) for 2025/2026 as required in terms section 53(1) (c) of the Municipal Finance Management Act, 2003 (MFMA) as stated above.

_________________						________________

Cllr B.A Radebe 						Date

Mayor: Dannhauser Local Municipality

- Municipal Manager’s Quality Assurance

Municipal Finance Management Act, 56 of 2003 (MFMA), section 69 (3) states the accounting officer must no later than 14 days after the approval of an annual budget submit to the mayor—

a) a draft service delivery and budget implementation plan for the budget year;

b) drafts of the annual performance agreements as required in terms of section 57(1)(b) of the Municipal Systems Act for the municipal manager and all senior managers

I, M.S Sithole , in my capacity as the Municipal Manager of the Dannhauser  Local Municipality thereby submit the revised 2025/2026 SDBIP to the Mayor/Council for consideration.

____________________ 						_______________

M.S Sithole								Date

Municipal Manager : Dannhauser Local Municipality

- MFMA Legislation

Section 1 of the Municipal Finance Management Act (MFMA), defines a SDBIP as a detailed plan approved by the mayor of a municipality in terms of Section 53(1)(c)(ii) for implementing the municipality’s planned service delivery and annual budget and must indicate (as part of the top-layer) the following:

a) projections for each month of:- i. ii. revenue to be collected by source; and operational and capital expenditure, by vote;

b) service delivery targets and performance indicators for each quarter; and 5 c) any other matters that may be prescribed and includes any revisions of such plan by the Mayor in terms of section 54(1)(c). In terms of MFMA section 53 (1) (c)(ii), the Mayor must, within 28 days after the adoption of the municipal budget, approve the municipality’s SDBIP.

5.  2025/2026 Service Delivery Budget Implementation Plan

| SDBIP NO | DIRECTORATE | IDP REF | STRATEGIC OBJECTIVE | STRATEGY | KPI(INITIAL) | KPI (REVISED) | ANNUAL TARGET(INITIAL) | ANNUAL TARGET (REVISED) | BUDGET | POE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KPA 1: Municipal Transformation and Institutional Development |  |  |  |  |  |  |  |  |  |  |  |
| Back to Basics: Building institutional resilience and administrative capability |  |  |  |  |  |  |  |  |  |  |  |
| MT 1 | Budget & Treasury Office | 1,1,1 | Regular monitor and evaluate performance of the Service Providers rendered services on behalf of Dannhauser municipality | Outsourced services effectively managed | Number monitored and evaluated performance assessment of the external Service Providers with signed SLA's | Number monitored and evaluated performance assessment of the external Service Providers with signed SLA's | 12x Performance Assessment reports external Service Providers in the Year ending 30 June 2026 | 12x Performance Assessment reports external Service Providers in the Year ending 30 June 2026 | NA | 12x Quarterly performance reports on external service providers |  |
| MT 2 | Corporate Services | 1,1,2 | To comply with WSP legislative requirements | Develop, consult and adoption of WSP and submission | Date of submission of the 2026/27 WSP | Date of submission of the 2026/27 WSP | Date of submission of the 2026/27 WSP to LGSETA by 30 April 2026 | Date of submission of the 2026/27 WSP to LGSETA by 30 April 2026 | NA | Proof of submission and the final 2026/27 WSP |  |
| MT 3 | Corporate Services | 1,1,2 |  | Implementation of 2026/27 WSP | Number of 2025/26 WSP training interventions offered | Number of 2025/26 WSP training interventions offered | 5x 2025/26 WSP training interventions offered in the year ending 30 June 2025 | 5x 2025/26 WSP training interventions offered in the year ending 30 June 2026 | NA | 1x training report |  |
| MT 4 | Corporate Services | 1,1,3 | Review and adoption of the 2025/26 organogram | Adoption of the 2026/27 organogram | Date of adoption of the 2026/27 organogram by council | Date of adoption of the 2026/27 organogram by council | Date of adoption 2026/27 organogram in the year ending 30 June 2026 | Date of adoption 2026/27 organogram in the year ending 30 June 2026 | NA | Approved organogram and council resolution |  |
| MT 5 | Corporate Services | 1,1,4 | Implement 2024/25 organogram | Implementation of the recruitment and selection policy | Number of filled vacant posts | Number of filled vacant posts | 8x filled vacant posts in the year ending 30 June 2026 | 8x filled vacant posts in the year ending 30 June 2026 | NA | 8x Appointment letters |  |
| MT 6 | Corporate Services | 1,1,5 | Adequately, develop, review, adopt and implementation of the municipal policies | Review and adoption of municipal policies | Number of reviewed and adopted municipal policies | Number of reviewed and adopted municipal policies | 64x municipal policies adopted in the year ending 30 June 2026 | 64x municipal policies adopted in the year ending 30 June 2026 | N/A | Council resolutions |  |
| MT 7 | Corporate Services | 1,1,6 | Develop records management system which in line with norms and standard for national archives | Development of records management strategy | Date of adoption of 2026/27 record management strategy | Date of adoption of 2026/27 record management strategy | Date of adoption of 2026/27 record management strategy in the year ending 30 June 2026 | Date of adoption of 2026/27 record management strategy in the year ending 30 June 2026 | N/A | Council resolution |  |
| MT 8 | Corporate Services | 1,1,6 |  | Development of records procedure manual | Date of adoption 2026/27 records procedure manual | Date of adoption 2026/27 records procedure manual | Date of adoption 2026/27 records procedure manual in the year ending 30 June 2026 | Date of adoption 2026/27 records procedure manual in the year ending 30 June 2026 | N/A | Council resolution |  |
| MT 9 | Corporate Services | 1,1,5 | Adequately, develop, review, adopt and implementation of the municipal policies | Review and adoption of the ICT strategy | Date of 2026/27 adoption of the ICT strategy | Date of adoption 2026/27 of the ICT strategy | Date of adoption of the ICT strategy in the year ending 30 June 2026 | Date of adoption of the ICT strategy in the year ending 30 June 2026 | N/A | Council resolution |  |
| MT 10 | Corporate Services | 1,1,5 |  | Review and adoption of the ICT plan | Date of 2026/27 adoption of the ICT plan | Date of 2026/27 adoption of the ICT plan | Date of adoption of the ICT plan in the year ending 30 June 2026 | Date of adoption of the ICT plan in the year ending 30 June 2026 | N/A | Council resolution |  |
| MT 11 | Corporate Services | 1,1,8 | To ensure a safe and secure municipal property through security services | Manage properties of municipality | Number of municipal properties managed through available support system | Number of municipal properties managed through available support system | 4x reports in the year ending 30 June 2026 | 16x municipal properties managed through available support system in the year ending 30 June 2026 | N/A | 4x progress reports |  |
| MT 12 | Planning and Economic Development | 1,1,9 | To facilitate the provision of integrated human settlement in-line with provincial and national norms and standards | Development of Housing Sector Plan | Date of Developing and adopting 2026/27 Housing sector plan in the year ending 30 June 2025. | Date of adoption 2025/26 Housing sector plan | Development and Adoption of 2025/2026 Housing Sector Plan By council in the year ending 30 June 2026. | Date of Adoption of 2025/26 Housing Sector Plan by council in the year ending 30 June 2026 | N/A | Council resolution |  |
| KPA 2: Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| Back to Basis: Delivering basic services |  |  |  |  |  |  |  |  |  |  |  |
| BSD 1 | Technical Services | 2,2,1 | Provide, improve and maintain new and existing infrastructure | Construction of Keelkeel Community Hall in ward 11 | 100% Overall construction progress made on the Construction of Keelkeel community hall in ward 11 in the year ending 30 June 2026 (PERCENTAGE) | Overall construction progress made on the Construction of Keelkeel community hall in ward 11 in the year ending 30 June 2026 | 100% Overall construction progress made on the Construction of Keelkeel community hall in ward 11 in the year ending 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Construction of Keelkeel community hall in ward 11 in the year ending 30 June 2026 | R3 500 000 | 3x Progress Reports on the % completion of the Construction of Community Hall, practical completion certificate |  |
| BSD 2 | Technical Services | 2,2,1 |  | Construction of Empungwini Community Hall in ward 01 | 100% Overall construction progress made on the Construction of Empungwini community hall in ward 01 in the year ending 30 June 2026 (PERCENTAGE) | Overall construction progress made on the Construction of Empungwini community hall in ward 01 in the year ending 30 June 2026 | 100% Overall construction progress made on the Construction of Empungwini community hall in ward 01 in the year ending 30 June 2026 (PERCENTAGE) | 30% Overall construction progress made on the Construction of Empungwini community hall in ward 01 in the year ending 30 June 2026 | R6 500 000 | 2x Progress Reports on the % completion of the Construction of Community Hall |  |
| BSD 3 | Technical Services | 2,2,1 |  | Construction of Flint community hall in ward 06 | 100% Overall construction progress made on the Construction of Flint community hall in ward 06 in the year ending 30 June 2026 (PERCENTAGE) | Overall construction progress made on the Construction of Flint community hall in ward 06 in the year ending 30 June 2026 | 100% Overall construction progress made on the Construction of Flint community hall in ward 06 in the year ending 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Construction of Flint community hall in ward 06 in the year ending 30 June 2026 | R6 500 000 | 4x Progress reports & practical completion certificate |  |
| BSD 4 | Technical Services | 2,2,1 |  | Construction of Hilltop community hall in ward 07 | Overall construction progress made on the Construction of Hilltop community hall in ward 07 in the year ending 30 June 2026 (PERCENTAGE) | Overall construction progress made on the Construction of Hilltop community hall in ward 07 in the year ending 30 June 2026 | 100% construction progress made on the Construction of Hilltop community hall in ward 07 in the year ending 30 June 2026 (PERCENTAGE) | 100% construction progress made on the Construction of Hilltop community hall in ward 07 in the year ending 30 June 2026 | R6 500 000 | 4x Progress reports & practical completion certificate |  |
| BSD 5 | Technical Services | 2,2,1 |  | Construction of ward 9 community | Percentage of construction of Ward 9 community Hall in the year ending 30 June 2025 | Percentage of construction of Ward 9 community Hall in the year ending 30 June 2025 | 100% construction progress made on the Construction of Hilltop community hall in ward 09 in the year ending 30 June 2026 (PERCENTAGE) | 90% construction progress made on the Construction of community hall in ward 09 in the year ending 30 June 2026 | R1080590,27 | 2x Progress reports |  |
| BSD 6 | Technical Services | 2,2,2 | To provide access to electricity infrastructure for households | Provision of Electrical Infrastructure to 100 households in ward 05 | 100X Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 05 | Number of planning and detailed designs for construction of electricity infrastructure in ward 5 | 100X Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 05 | 1x planning and detailed designs for construction of electricity in ward 5 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 7 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 10 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 10 | Number of electricity poles to be provided to households in ward 10 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 10 | 30x electricity poles to be provided to households ward 10 in the year ending 30 June 2026 | R2 100 000 | Appointment letter & 1x progress report |  |
| BSD 8 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 01 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 01 | Number of planning and detailed designs for construction of electricity infrastructure in ward 1 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 01 | 1x planning and detailed designs for construction of electricity in ward 1 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 9 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 06 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 06 | Number of planning and detailed designs for construction of electricity infrastructure in ward 6 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 06 | 1x planning and detailed designs for construction of electricity in ward 6 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 10 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 07 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 07 | Number of planning and detailed designs for construction of electricity infrastructure in ward 7 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 07 | 1x planning and detailed designs for construction of electricity in ward 7 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 11 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 09 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 09 | Number of planning and detailed designs for construction of electricity infrastructure in ward 9 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 09 | 1x planning and detailed designs for construction of electricity in ward 9 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 12 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 11 | 100x Number of households to be supplied with new electricity connections within municipal standard and timeframes by 30 June 2026 in ward 11 | Number of planning and detailed designs for construction of electricity infrastructure in ward 11 | 100x Number of households to be supplied with new electricity connections within municipal standard and timeframes by 30 June 2026 in ward 11 | 1x planning and detailed designs for construction of electricity in ward 11 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 13 | Technical Services | 2,2,2 |  | Provision of Electrical Infrastructure to 100 households in ward 13 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 13 | Number of planning and detailed designs for construction of electricity infrastructure in ward 13 | 100x Number of households to be supplied with new electrical infrastructure within municipal standard and timeframes by 30 June 2026 in ward 13 | 1x planning and detailed designs for construction of electricity in ward 13 in the year ending 30 June 2026 | R2 100 000 | Planning & designs |  |
| BSD 14 | Technical Services | 2,2,2 |  | Provision of 2x high mast lights in ward 03 | 2x Number of areas to be supplied with new high mast lights within municipal standard and timeframes by 30 June 2026 in ward 03 | Percentage of 2x completion high mast lights within municipal standard and timeframes by 30 June 2026 in ward 03 | 2x Number of areas to be supplied with new high mast lights within municipal standard and timeframes by 30 June 2026 in ward 03 | 15% high mast lights within municipal standard and timeframes by 30 June 2026 in ward 03 | R1 000 000 | Appointment letter & 1x progress report |  |
| BSD 15 | Technical Services | 2,2,1 | Provide, improve and maintain new and existing infrastructure | Upgrading of Durnacol Urban Roads in ward 02 | 100% Overall construction progress made on the Upgrading of Durnacol Urban Roads in ward 02 by 30 June 2026 (PERCENTAGE) | % Overall construction progress made on the Upgrading of Durnacol Urban Roads in ward 02 by 30 June 2026 | 100% Overall construction progress made on the Upgrading of Durnacol Urban Roads in ward 02 by 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Upgrading of Durnacol Urban Roads in ward 02 by 30 June 2026 | R9 400 000 | 3x Progress Report and practical completion certificate |  |
| BSD 16 | Technical Services | 2,2,1 |  | Upgrading of Vanjazi Gravel Access Road in ward 12 | 100% Overall construction progress made on the Upgrading Vanjazi Gravel Access Road in ward 12 by 30 June 2026 (PERCENTAGE) | % Overall construction progress made on the Upgrading Vanjazi Gravel Access Road in ward 12 by 30 June 2026 | 100% Overall construction progress made on the Upgrading Vanjazi Gravel Access Road in ward 12 by 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Upgrading Vanjazi Gravel Access Road in ward 12 by 30 June 2026 | R5 500 000 | 3x Progress Report on % and practical completion certificate |  |
| BSD 17 | Technical Services | 2,2,1 |  | Upgrading of Eastborne Access Gravel Road in ward 10 | 100% Overall construction progress made on the Upgrading of Eastbourne Access Gravel Road in ward 10 by 30 June 2026 (PERCENTAGE) | % Overall construction progress made on the Upgrading of Eastborne Access Gravel Road in ward 10 by 30 June 2026 | 100% Overall construction progress made on the Upgrading of Eastborne Access Gravel Road in ward 10 by 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Upgrading of Eastborne Access Gravel Road in ward 10 by 30 June 2026 | R3 500 000 | 3x Progress Report on % and practical completion certificate |  |
| BSD 18 | Technical Services | 2,2,1 |  | Upgrading of Culvert bridge in ward 07 | 100% Overall construction progress made on the Upgrading of Culvert bridge in ward 07 by 30 June 2026 (PERCENTAGE) | % Overall construction progress made on the Upgrading of Culvert bridge in ward 07 by 30 June 2026 | 100% Overall construction progress made on the Upgrading of Culvert bridge in ward 07 by 30 June 2026 (PERCENTAGE) | 100% Overall construction progress made on the Upgrading of Culvert bridge in ward 07 by 30 June 2026 | R2 500 000 | appointment letter & 1x progress report |  |
| BSD 19 | Technical Services | 2,2,1 |  | Construction of Ward 8 Creche | 50% construction progress made on the construction of Creche in ward 08 (PERCENTAGE) | % construction progress made on the construction of Creche in ward 08 | 50% construction progress made on the construction of Creche in ward 08 | 20% construction progress made on the construction of Creche in ward 08 in the year ending 30 June 2026 | 2 000 000 | Appointment letter & 1x progress report |  |
| BSD 20 | Technical Services | 2,2,1 |  | Construction of Ward 5 Creche | 50% construction progress made on the construction of Creche in ward 05 (PERCENTAGE) | % construction progress made on the construction of Creche in ward 05 | 50% construction progress made on the construction of Creche in ward 05 | 20% construction progress made on the construction of Creche in ward 05 in the year ending 30 June 2026 | 2 000 000 | 4x progress reports |  |
| BSD 21 | Technical Services | 2,2,1 |  | Construction of Ward 12 Creche | 50% construction progress made on the construction of Creche in ward 12 (PERCENTAGE) | % construction progress made on the construction of Creche in ward 12 | 50% construction progress made on the construction of Creche in ward 12 | 20% construction progress made on the construction of Creche in ward 12 in the year ending 30 June 2026 | 2 000 000 | Appointment letter & 1x progress report |  |
| BSD 22 | Technical Services | 2,2,1 |  | Construction of Municipal Testing Grounds | percentage completion of testing centre in ward 2 | percentage completion of testing centre in ward 2 | 30% Completion of the Testing centre in ward 2 | 15% Completion of the Testing centre in ward 2 in the year ending 30 June 2026 | R 2 000 000.00 | Request for advertisement & 1x progress report |  |
| BSD 23 | Community Services | 2,2,3 | To ensure safe and clean environment within Dannhauser Municipal Area | Regular provision of waste removal services within Dannhauser municipal area uninterrupted | Number of waste removal services as per approved schedule for the designated areas | Number of reports on waste removal services provided as per approved schedule | 4x quarterly reports for the year ending 30 June 2026 | 4x reports on waste removal services provided as per approved schedule in the year ending 30 June 2026 | NA | 4x Detailed report Quarterly |  |
| BSD 24 | Community Services | 2,2,3 |  | Promote health and safe environment | Number of cleaning and awareness campaign conducted | Number of cleaning and awareness campaign conducted | 4x number of cleaning and awareness campaign conducted in the year ending 30 June 2026 | 4x cleaning and awareness campaign conducted in the year ending 30 June 2026 | NA | 4x Attendance register & detailed report |  |
| BSD 25 | Community Services | 2,2,4 | Access to public library services within the municipal area | Accessibility and Management of library information services. Provision of library lending, computer and internet services | Number of users accessing computer services | Number of reports on users accessing computer services | 4x progress report & attendance register in the year ending 30 June 2026 | 4x reports on users accessing computer services in the year ending 30 June 2026 | NA | 4x progress report, attendance register |  |
| BSD 26 | Community Services | 2,2,4 |  |  | Number of computer training programs conducted and monitored | Number of computer training programs conducted and monitored | 2x computer training programme conducted and monitored progress report in the year ending 30 June 2026 | 2x computer training programme conducted and monitored in the year ending 30 June 2026 | R30 000 | 2x progress report, attendance register & invitation |  |
| BSD 27 | Community Services | 2,2,4 |  |  | Number of monitored and management of lending library materials and registered users | Number of reports on monitoring and management of lending library materials and registered users | 4x reports in the year ending 30 June 2026 | 4x reports on monitoring and management of lending library materials and registered users in the year ending 30 June 2026 | NA | 4x Reports |  |
| BSD 28 | Community Services | 2,2,5 | Provision of law enforcement/by-laws and crime prevention | Conduct multidisciplinary roadblocks | Number of conducted stop and search operations, visibility and walk-about | Number of conducted stop and search operations, visibility and walk-about | 4x stop and search operations conducted in the year ending 30 June 2026 | 4x stop and search operations conducted in the year ending 30 June 2026 | N/A | 4x Reports and roadblock registers |  |
| BSD 29 | Community Services | 2,2,6 | To ensure the Implementation of the gazetted Animal Pound By-Law and its enforcement within the municipal jurisdiction | Animal Pound By-Law Enforcement | Number of reports on reducing the high rate of animal astray within the designated municipal area | Number of reports on reducing the high rate of animal astray within the designated municipal area | 4 x animal pound progress report in the year ending 30 June 2026 | 4x report on reducing the high rate of animal astray within the designated municipal area in the year ending 30 June 2026 | R1 370 340 | 4 x quarterly progress reports |  |
| BSD 30 | Community Services | 2,2,7 | To respond on the reported disaster related incidents and the provision of relief to victims of disaster | Disaster reported incidences managed effectively | Number of reported, assessed and responded incidents of disaster | Number of reports on assessment and responds to incidents of disaster | 4x Quarterly reports on intervention of reported incidents and relief support provided for the year ending 30 June 2026 | 4x reports on assessment and responds to incidents of disaster in the year ending 30 June 2026 | 1 000 000 | 4x Incident Response Reports |  |
| BSD 31 | Community Services | 2,2,3 | To ensure safe and clean environment within Dannhauser Municipal Area | Provision of Free Basic Services (Waste removal) | Percentage of registered indigent households earning less than R5 000 per month that received free basic services, including refuse removal, by 30 June 2026 | Percentage of registered indigent households earning less than R5 000 per month that received free basic services, including refuse removal | 100% of registered indigent households earning less than R5 000 per month that received free basic services, including refuse removal, by 30 June 2026. | 100% of registered indigent households earning less than R5 000 per month that received free basic services, including refuse removal, in the year ending 30 June 2026. | N/A | 4x waste removal report and indigent list |  |
| BSD 32 | Planning and Economic Development | 2,2,8 | To facilitate the provision of integrated human settlement in line with provincial and national norms and standards | To address housing backlog in line with natural disasters | Construction of 30 Disaster/Relief Shelters in the year ending 30 June 2026. | Percentage completion on the construction of 30 Disaster Shelters(1,3,4,5,6&8) | Progress report on completion of 30 Disaster/Relief shelters in the year ending 30 June 2026. | 50% completion on the construction of 30 Disaster Shelters (1,3,4,5,6&8) by 30 June 2026 | R3, 231 782,50 | 2x progress report and close-out report |  |
| BSD 33 | Planning and Economic Development | 2,2,8 |  | Rural and urban Housing Project: Implementation | Construction of 30 Disaster/Relief Shelters in the year ending 30 June 2026. | Preliminary planning and design studies for the construction of disaster/relief shelters in all ward | 4x Progress report on monitoring and implementation of rural and urban housing projects. | Completion preliminary planning and design for 15 disaster/relief shelters in the year ending 30 June 2026 | 2 500 000 | Appointment of service provider, Beneficiary administration & Geo-technical report |  |
| BSD 34 | Planning and Economic Development | 2,2,8 |  |  | Construction of 30 Disaster/Relief Shelters in the year ending 30 June 2026. | Facilitate and Monitor implementation of 6x human settlement projects through regular project steering committee meetings in ward 2, 3, 5, 9, 10 and 13 | 24x progress reports on the 6 human settlement projects in the year ending 30 June 2026. | Conduct 24x project steering committee meetings (average 4 per project) to monitor progress in six human settlement projects in the year ending 30 June 2026. | N/A | Agenda, minutes and attendance register |  |
| KPA 3: Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |
| Back to Basics: Promoting Sound Financial Management |  |  |  |  |  |  |  |  |  |  |  |
| LED 1 | Planning and Economic Development | 3,3,1 | Implement comprehensive LED strategy for the growth of all economic sectors in Dannhauser municipal area | Ensuring LED programmes are implemented, monitored, reviewed and evaluated. | The establishment of LED Forum and sub committees meeting held quarterly in the year ending 30 June 2026. | Number of LED sub-committees meetings held quarterly | 2x LED Forum meeting per quarter(Q2 and Q4) and 4x LED sub committees meeting in the year ending 30 June 2026 | 4x LED sub-committees meeting in the year ending 30 June 2026 | N/A | Agenda, minutes and attendance register |  |
| LED 2 | Planning and Economic Development | 3,3,1 |  |  | Number of formal businesses issued with business licences in terms of business Act 71 of 1991 in the year ending 30 June 2025 | Percentage of business license issued to formal businesses in terms of business Act 71 of 1 | 4x Businesses licenses issued to formal Businesses in terms Business Act 71 of 1991 in the year ending 30 June 2026. | 100% of business license issued to formal businesses in terms of business Act 71 of 1in the year ending 30 June 2026. | N/A | Business licenses and proof of payment and Application Register. |  |
| LED 3 | Planning and Economic Development | 3,3,1 |  |  | Number of informal businesses issued with business licences in terms of informal economic policy in the year ending 30 June 2025 | Percentage of permit applications issued with trading permits in terms of informal economic policy | 10x trading permits issued to informal businesses in the year ending 30 June 2026. | 100% of permit applications issued with trading permits in terms of informal economic policy in the year ending 30 June 2026. | N/A | Trading permit and proof of payment and application register |  |
| LED 4 | Planning and Economic Development | 3,3,1 |  |  | Monitor implementation of the social labour plans (SLP) for all mines within Dannhauser area in the year ending 30 June 2025 | Percentage of registered mines in the Dannhauser area with quarterly monitoring reports on Social Labour Plan (SLP) project implementation, in terms of the Mineral and Petroleum Resources Development Act (MPRDA). | 4x progress report on implementation on the SLPs in the year ending 30 June 2026 | 100% Percentage of registered mines in the Dannhauser area with quarterly monitoring reports on Social Labour Plan (SLP) project implementation, in terms of the Mineral and Petroleum Resources Development Act (MPRDA).in the year ending 30June 2026 | N/A | 4x progress report |  |
| LED 5 | Planning and Economic Development | 3,3,1 |  |  | The development of shopping centre by the year ending 30 June 2026 | Facilitate and monitor the development of a shopping centre in Ward 2 through quarterly reporting and milestone tracking | 4x progress report on development of shopping centre by the year | 4x progress report on pre-planning studies for development of shopping centre in the year ending 30 June 2026 | N/A | 4x progress report |  |
| LED 6 | Planning and Economic Development | 3,3,2 | Capacity building for local Economic Development related programs | Implement LED related programs | Monitor the Implementation of LED Empowerment related programs for SMMES by the year ending 30 June 2026 | Number of LED Empowerment related programs implemented for SMMES | 4x Progress report on the implementation of LED related programs in the year ending 30 June 2026. | 4x LED related programs implemented in the year ending 30 June 2026. | R3 000 000.00 | Agenda and register |  |
| LED 7 | Community Services | 3,3,3 | To promote employment opportunities through municipal EPWP programs and projects. | To implement and monitor municipal EPWP program | Number of jobs created through EPWP | Number of jobs created through EPWP | 587 EPWP jobs to be created in the year ending 30 June 2026 | 570 EPWP jobs to be created in the year ending 30 June 2026 | 6 500 000 | 4x reports and the list of EPWP recruited |  |
| LED 8 | Community Services | 3,3,4 | Create job opportunities, safe & clean environment | Implementation of recycling at a landfill site informal & formal waste picker | Number of recycled wastes in tonnage | Number of recycled wastes in tonnage | 4x number of recycle waste in tonnage in the year ending 30 June 2026 | 4x number of recycle waste in tonnage in the year ending 30 June 2026 | N/A | 4x Report |  |
| KPA 4: |  |  |  |  |  |  |  |  |  |  |  |
| BACK TO BASICS |  |  |  |  |  |  |  |  |  |  |  |
| GG 1 | Budget and Treasury Office | 4,4,1 | To ensure progressive compliance with institutional and governance requirements | Budgeting | Date of Adoption of the 2025/26 Adjustment Budget by Council | Date of Adoption of the 2025/26 Adjustment Budget by Council | Adoption of 2025/26 Adjustment Budget by Council by 28 February 2026 | Adoption of 2025/26 Adjustment Budget by Council by 28 February 2026 | NA | Council Resolution |  |
| GG 2 | Budget and Treasury Office | 4,4,1 |  |  | Date of adoption of the 2026/27 draft Budget by Council | Date of adoption of the 2026/27 draft Budget by Council | Date of adoption of the 2026/27 Draft Budget by Council 31 March 2026 | Date of adoption of the 2026/27 Draft Budget by Council 31 March 2025 | NA | Council Resolution and proof of submission to NT |  |
| GG 3 | Budget and Treasury Office | 4,4,1 |  |  | Date of Approval of the 2026/27 Final Budget by Council | Date of Approval of the 2026/27 Final Budget by Council | Approval of 2026/27 Final Budget by Council 31 May 2026 | Approval of 2026/27 Final Budget by Council 31 May 2026 | NA | Council Resolution and proof of submission to NT |  |
| GG 4 | Budget and Treasury Office | 4,4,1 |  | Financial Reporting | Submit Section 71 reports (including SCM/Expenditure/Revenue, reporting) to Mayor, National/Provincial treasury, MPAC, Exco, BTO and council | Number of submitted Section 71 reports (including SCM/Expenditure/Revenue, reporting) to Mayor, National/Provincial treasury, MPAC, Exco, BTO and council | Submission of 12 X Monthly Section 71 reports to Mayor and Provincial Treasury within 10 working days after the end of the month in the year ending 30 June 2026 | Submission of 12 X Monthly Section 71 reports to Mayor and Provincial Treasury within 10 working days after the end of the month in the year ending 30 June 2026 | NA | Section 71 Reports and proof of submission |  |
| GG 5 | Budget and Treasury Office | 4,4,1 |  |  | Date of submission of section 72 report to Mayor, National/Provincial treasury, Exco, BTO, MPAC and Council (2025/26) to Council by MM | Date of submission of section 72 report to Mayor, National/Provincial treasury, Exco, BTO, MPAC and Council (2025/26) to Council by MM | Submission of Sect 72 Report to the Mayor by 25 January 2026 | Date of submission of Sect 72 Report to the Mayor by 25 January 2026 | NA | Council Resolution and proof of Submission |  |
| GG 6 | Budget and Treasury Office | 4,4,1 |  |  | Date of Submission of 2024/25 Annual Financial Statements to AG | Date of Submission of 2024/25 Annual Financial Statements to AG | Submission of 2024/25 AFS to AG by 31 Aug 2025 | Date of submission of 2024/25 AFS to AG by 31 Aug 2025 by 31 August 2025 | NA | Copy of AFS and Letter of Acknowledgement by AG |  |
| GG 7 | Budget and Treasury Office | 4,4,1 |  | Management of Indigent households | Date of Adoption of the 2026/27 Updated and Reviewed Indigent Policy by Council | Date of Adoption of the 2026/27 Updated and Reviewed Indigent Policy by Council | Adoption of the 2026/27 Updated and reviewed indigent Policy by Council in the year ending 30 June 2026 | Adoption of the 2026/27 Updated and reviewed indigent Policy by Council in the year ending 30 June 2026 | NA | Council resolution |  |
| GG 8 | Budget and Treasury Office | 4,4,2 | To provide reasonable assurance on the adequacy and effectiveness of internal control systems | Asset Management Review | Number asset Verification conducted and performed | Number asset Verification conducted and performed | 1x Asset Verification conducted and performed in the year ending 30 June 2026 | 1x 2024/2025 Asset Verification conducted and performed in the year ending 30 June 2026 | NA | Asset Verification Report |  |
| GG 9 | Community Services | 4,4,3 | To provide disaster prevention, mitigation and preparedness measures. | Effectively co-ordinate and provide awareness programs on disaster management | Number of awareness programs co-ordinated and conducted | Number of disaster awareness programs co-ordinated and conducted | 4x awareness programmes conducted and monitored in the year ending 30 June 2026 | 4x disaster awareness programs co-ordinated and monitored in the year ending 30 June 2026 | R50 000 | 4x awareness reports and attendance register |  |
| GG 10 | Community Services | 4,4,4 | Develop, review and adopt sector plans related to department | Review and adoption of the disaster management sector plan | Date and Adoption of the 2026/2027 disaster management sector plan by council | Date and Adoption of the 2026/27 disaster management sector plan by council | Date for adoption in the year ending 30 June 2026 | Date and Adoption of the 2026/27 disaster management sector plan by council in the year ending 30 June 2026 | NA | Council resolution |  |
| GG 11 | Community Services | 4,4,4 |  | Review, adoption of Integrated Waste Management Plan (IWMP) | Date of adoption for 2026/27 IWMP | Date of adoption for 2026/27 IWMP | Date for adoption in the year ending 30 June 2026 | Date for adoption 2026/27 IWMP in the year ending 30 June 2026 | N/A | Council resolution |  |
| GG 12 | Community Services | 4,4,4 |  | Review and adoption of the cemetery plan | Date of adoption 2026/27 of the cemetery plan | Date of adoption 2026/27 of the cemetery plan | Date for adoption in the year ending 30 June 2026 | Date for adoption cemetery plan in the year ending 30 June 2026 | N/A | Council resolution |  |
| GG 13 | Community Services | 4,4,4 |  | Development and adoption environmental management plan | Date of adoption 2026/27 of the environmental management plan | Date of adoption 2026/27 of the environmental management plan | Date for adoption in the year ending 30 June 2026 | Date for adoption environmental management plan in the year ending 30 June 2026 | N/A | Council resolution |  |
| GG 14 | Community Services | 4,4,4 |  | development, adoption and gazette of waste management by-laws | Date of adoption and gazette 2026/27 of the waste management by-laws | Date of adoption and gazette 2026/27 of the waste management by-laws | Date for adoption in the year ending 30 June 2026 | Date of adoption and gazette 2026/27 of the waste management by-laws in the year ending 30 June 2026 | N/A | Council resolution |  |
| GG 15 | Community Services | 4,4,5 | Implementation of IGR framework | Implementation of Operation Sukumasakhe | Number of Operation Sukumasakhe meetings attended | Number of Operation Sukumasakhe meetings attended | 4x Sukumasakhe meetings in the year ending 30 June 2026 | 4x Sukumasakhe meetings attended in the year ending 30 June 2026 | N/A | Attendance register |  |
| GG 16 | Community Services | 4,4,5 |  | Co-ordinate and convene of the local disaster management advisory forum | Number of meetings of local disaster advisory forum | Number of meetings of local disaster advisory forum | 4x meetings of local disaster advisory forum in the year ending 30 June 2026 | 4x local disaster advisory forum meeting conducted in the year ending 30 June 2026 | N/A | Attendance register |  |
| GG 17 | community services | 4,4,6 | To direct traffic and improve safety and security | Traffic Services ( learners, drivers and motor licensing) | Number of Traffic Services report submitted to portfolio and Exco | Number of Traffic Services report submitted to portfolio and Exco | 4x traffic services report submitted to Portfolio and Exco in the year ending 30 June 2026 | 4x traffic services report submitted to Portfolio and Exco in the year ending 30 June 2026 | NA | 4 x Law enforcement Reports |  |
| GG 18 | Community Services | 4,4,7 | To market the library resources and facilities to its maximum usage | To facilitate library orientation and outreach programmes in local schools and community | Number of programmes conducted during library week | Number of report on programmes conducted during library week | 1x Reports of library week program in the year ending 30 June 2026 | 1x report of library week program in the year ending 30 June 2026 | R30 000 | attendance register, invitation and 1x report |  |
| GG 19 | Office of the Municipal Manager | 4,4,8 | To ensure the functional of Audit and Performance Committee | Implementation of Risk Management Action Plan | Number on implementation of the 2024/25 Risk Management Action Plan | Number of risk management progress reports and risk register submitted | 4x progress report on implementation plan of Risk Management Action Plan In the year ending 30 June 2026 | 4x risk progress reports submitted and risk register in the year ending 30 June 2026 | NA | 4x Risk Management Progress Reports and Risk Register |  |
| GG 20 | Office of the Municipal Manager | 4,4,8 |  | Achieve Unqualified Audit Opinion | % implementation of the AGSA action plan | % implementation of the AGSA action plan | 100% implementation of the 2024/25 AGSA Action Plan in the year ending 30 June 2026 | 100% implementation of the 2024/2025 AGSA Action Plan in the year ending 30 June 2026 | NA | 2 x Progress Reports |  |
| GG 21 | Office of the Municipal Manager | 4,4,1 | To ensure progressive compliance with institutional and governance requirements | Review and adoption of 2025/26 revised SDBIP | Date of review and adoption of 2025/26 revised SDBIP | Date of review and adoption of 2025/26 revised SDBIP | Date of adoption of 2025/26 revised SDBIP by 28 Feb 2026 | Date of adoption of 2025/26 revised SDBIP by 28 Feb 2026 | NA | Council resolution |  |
| GG 22 | Office of the Municipal Manager | 4,4,1 |  | Monitor the performance assessments for the year ending 2025/2026 (MM & Directors) | Number of performance assessments conducted | Number of performance assessments conducted | 4x quarterly Performance assessments to be conducted (2x Informal/verbal & 2 x Formal) in the year ending 30 June 2026 | 1x 2024/25 Performance assessments to be conducted in the year ending 30 June 2026 | NA | Panel attendance registers and Appraisal |  |
| GG 23 | Office of the Municipal Manager | 4,4,1 |  | Adoption of Mid-year performance report for the financial year 2025/2026 | Date of adoption of 2025/26 Mid-year Performance Report by council | Date of adoption of 2025/26 Mid-year Performance Report by council | Submit 2025/26 Mid-year performance report and adoption by Council by the 25 January 2026 | Adoption of 2025/26 Mid-year performance report by Council 25 January 2026 | NA | council resolution |  |
| GG 24 | Office of the Municipal Manager | 4,4,1 |  | Develop, submission and adoption of 2026/27 SDBIP | Date of submission of the 2026/27 Draft SDBIP to the Mayor by MM within 14days after adoption of the Final 2026/27 Budget and IDP Review | Date of submission of the 2026/27 Draft SDBIP to the Mayor by MM within 14 days after adoption of the Draft 2026/2027 Budget and IDP Review | Submission of the 2026/27 Draft SDBIP to the Mayor by MM within 14 days after approval of the Final Budget and IDP Review in the year ending 30 June 2026 | Submission of the 2026/27 Draft SDBIP to the Mayor by MM within 14 days after approval of the Draft Budget and IDP Review in the year ending 30 June 2026 | NA | Proof of submission of the 2026/27 Draft SDBIP to the Mayor by MM |  |
| GG 25 | Office of the Municipal Manager | 4,4,1 |  |  | Date of approval of 2026/27 Final SDBIP by the Mayor/Council | Date of approval of 2025/27 Final SDBIP by the Mayor/Council | Approval of 2026/27 Final SDBIP by Mayor/Council within 28 days after 2026/27 budget approval in the year ending 30 June 2026 | Approval of 2026/27 Final SDBIP by Mayor/Council within 28 days after 2026/27 budget approval in the year ending 30 June 2026 | NA | Council Resolution |  |
| GG 26 | Office of the Municipal Manager | 4,4,1 |  | Adoption of the 2024/25 Annual Report | Date of Adoption of the 2024/25 Draft Annual Report by Council | Date of Adoption of the 2024/25 Draft Annual Report by Council | Date of Adoption of the 2024/25 Draft Annual Report by Council in the year ending 30 June 2026 | Date of Adoption of the 2024/25 Draft Annual Report by Council in the year ending 30 June 2026 | N/A | Council Resolution |  |
| GG 27 | Office of the Municipal Manager | 4,4,1 |  |  | Date of Adoption of the 2024/25 Oversight Report(OR) by Council | Date of Adoption of the 2024/25 Oversight Report by Council | Adoption of the Oversight Report 2024/2025 by Council in the year ending 30 June 2026 | Adoption of the Oversight Report 2024/2025 by Council in the year ending 30 June 2026 | N/A | Council Resolution |  |
| GG 28 | Office of the Municipal Manager | 4,4,1 |  |  | Date of Adoption of the 2024/25 Final Annual Report by Council | Date of Adoption of the 2024/25 Final Annual Report by Council | Date of Adoption of the 2024/25 Final Annual Report by Council in the year ending 30 June 2026 | Date of Adoption of the 2024/25 Final Annual Report by Council in the year ending 30 June 2026 | N/A | Council Resolution |  |
| GG 29 | Office of the Municipal Manager | 4,4,1 |  | Develop and adoption of 2026/27 IDP | Date of adoption of the 2026/27 Draft IDP by Council | Date of adoption of the 2026/27 Draft IDP | Date of adoption of the 2026/27 Draft IDP by Council by 31 March | Date of adoption of the 2026/27 Draft IDP by Council by 31 March | N/A | Council Resolution |  |
| GG 30 | Office of the Municipal Manager | 4,4,1 |  |  | Date of Adoption of 2026/27 Final IDP by Council | Date of Adoption of 2026/27 Final IDP by Council 31 May 2026 | Date of adoption of 2026/27 Final IDP by Council in the year ending 30 June 2026 | Date of adoption of 2026/27 Final IDP by Council in 31 May 2026 | N/A | Council Resolution |  |
| GG 31 | Office of the Municipal Manager | 4,4,9 | Ensure a participative/consultation, transparent and accountable governance | Effective and functional Ward Committees System | Number of Ward Committee meetings conducted (1-13) | Number of Ward Committee meetings conducted (ward 1-13) | 156x Number of Ward Committee meetings conducted in the year ending 30 June 2026 | 156x Number of Ward Committee meetings conducted (12x per ward) in the year ending 30 June 2026 | NA | Attendance report and Minutes |  |
| GG 32 | Office of the Municipal Manager | 4,4,9 |  | Ensure the existence and functionality of the public participation structures. | Number of IDP RF conducted | Number of IDP RF conducted | 2x RF meetings conducted in the year ending 30 June 2026 | 2x IDP RF meetings conducted in the year ending 30 June 2026 | NA | Attendance register, Minutes |  |
| GG 33 | Office of the Municipal Manager | 4,4,9 |  |  | Number of steering committee meeting conducted | Number of IDP steering committee meeting conducted | 4x of steering committee meeting conducted in the year ending 30 June 2026 | 4x of IDP steering committee meeting conducted in the year ending 30 June 2026 | NA | Attendance register, Minutes |  |
| GG 34 | Office of the Municipal Manager | 4,4,9 |  |  | Number of meetings conducted with MRRT | Number of MRRT meetings conducted | 4x meetings conducted with MRRT in the year ending 30 June 2026 | 4x MRRT meetings conducted in the year ending 30 June 2026 | NA | Attendance register and Minutes & Report |  |
| GG 35 | Office of the Municipal Manager | 4,4,9 |  | Improve the public participation and communication processes | Number of ward constituency meetings conducted | Number of ward constituency meetings conducted | 26x ward constituency and engagement meeting conducted in the year ending 30 June 2026 | 26x ward constituency and engagement meeting conducted in the year ending 30 June 2026 | NA | Attendance register, Minutes & Report |  |
| GG 36 | Office of the Municipal Manager | 4,4,8 | To ensure the functional of Audit and Performance Committee | Functional Audit and Performance Committee | Number of Quarterly Audit and Performance Committee meetings coordinated | Number of Audit and Performance Committee meetings co-ordinated | 4x AC Quarterly meeting in the year ending 30 June 2026 | 4x AC meeting in the year ending 30 June 2026 | NA | Attendance register, agenda, Minutes |  |
| GG 37 | Office of the Municipal Manager | 4,4,10 | Regular issued, compile media and communication statements by the Municipality on matters of governance | Communication and media release statements by the Municipality | Number of media and communication statements published | Number of media and communication statements published | 4x reports of Media statement and communication report issued in the year ending 30 June 2026 | 4x media statement and communication statements issued in the year ending 30 June 2026 | 500 000 | 4x media and communication statements issued and 4x reports |  |
| GG 38 | Office of the Municipal Manager | 4,4,11 | Implement Special Programmes as per approved Budget and IDP | Coordinate and implement Special Programmes as per approved plans and structures | Number of Special Programmes Coordinated and implemented as per approved plan | Number of Special Programmes Coordinated and implemented as per approved plan | 4x reports on Special Programmes coordinated and conducted in the year ending 30 June 2026 | 4x reports on Special Programmes coordinated and conducted in the year ending 30 June 2026 |  | Report, Agenda and attendance register |  |
| GG 39 | Office of the Municipal Manager | 4,4,5 | Implementation of IGR framework | Coordinate and attendance of IGR Structures through invitation from stakeholders | Number of DDM Meetings coordinated and attended | Number of DDM Meetings coordinated and attended | 4x report DDM Meetings coordinated and attended in the year ending 30 June 2026 | 4x report DDM Meetings coordinated and attended in the year ending 30 June 2026 | NA | Agenda and invitation |  |
| GG 40 | Office of the Municipal Manager | 4,1,12 | To ensure that the municipality has zero litigations gains | Ensure compliance with all South African laws and legislations | Number of litigations attended to | Number of litigations attended to | 4x progress reports in the year ending 30 June 2026 | 4x progress reports in the year ending 30 June 2026 | N/A | 4x Reports |  |
| GG 41 | Corporate Services | 4,4,1 | To ensure progressive compliance with institutional and governance requirements | Implementation of the standing rules of order | Number of councils sitting as per approved schedule | Number of council sitting as per approved schedule | 4x progress reports in the year ending 30 June 2026 | 12x of council sitting convened in the year ending 30 June 2026 | N/A | Notice of meeting and attendance Registers. |  |
| GG 42 | Corporate Services | 4,4,1 |  |  | Number of EXCO sitting as per approved schedule | Number of EXCO sitting as per approved schedule | 4x reports of council meeting convened in the year ending 30 June 2026 | 12x EXCO convened in the year ending 30 June 2026 | N/A | Notice of meeting and attendance Registers. |  |
| GG 43 | Corporate Services | 4,4,1 |  |  | Number of MPAC sitting as per approved schedule | Number of MPAC sitting held | 4x reports EXCO convened in the year ending 30 June 2026 | 4x MPAC convened in the year ending 30 June 2026 | N/A | Notice of meeting and attendance Registers. |  |
| GG 44 | Corporate Services | 4,4,1 |  |  | Number of Technical, Community, Corporate, Planning & Economic Development and Budget & Treasury Office sitting as per approved schedule | Number of Technical, Community, Corporate, Planning & Economic Development and Budget & Treasury Office sitting as per approved schedule | 4x reports MPAC convened in the year ending 30 June 2026 | 20x portfolio committees meeting convened in the year ending 30 June 2026 | N/A | Notice of meeting and attendance Registers. |  |
| GG 45 | Corporate Services | 4,4,1 |  | Adequately implementation of the policy and compliance | Number of monitored and maintained municipal fleet | Number of municipal fleet vehicle monitored and maintained | 4x progress reports in the year ending 30 June 2026 | 30x monitored and maintained municipal fleet vehicle in the year ending 30 June 2026 | NA | 4x progress reports |  |
| GG 46 | Corporate Services | 4,4,1 |  | Implementation of OHS in line with national health regulations | Number of Roll-out OHS programs conducted | Number of Roll-out OHS programs conducted | 4x Number of Roll-out OHS programs conducted in the year ending 30 June 2026 | 4x Roll-out OHS programs conducted in the year ending 30 June 2026 | NA | Annual schedule and attendance register/ checklist |  |
| GG 47 | Corporate Services | 4,4,1 |  | Provision of administration support to council | Number of administration support provided to Council | Number of administrative and governance support provided to municipal council | 4x Report of administration provided to Council in the year ending in 30 June 2026 | 4x administrative and governance support provided to municipal council in the year ending in 30 June 2026 | NA | 4x Reports |  |
| GG 48 | Planning and Economic Development | 4,4,1 |  | Rural and urban Housing Project: Implementation | Housing forum meetings held quarterly in the year ending 30 June 2026. | Number of housing forum meetings held quarterly | 4x Progress report on monitoring and implementation of rural and urban housing projects. | 4x housing forum meetings held in the year ending 30 June 2026 | N/A | Agenda, minutes and attendance register |  |
| KPA 5: Cross Cutting |  |  |  |  |  |  |  |  |  |  |  |
| Back to Basis: Delivering Basic Services |  |  |  |  |  |  |  |  |  |  |  |
| CC 1 | community Services | 5,5,1 | Maintenance of public areas & cemeteries | Greening & Gardening in municipal and public areas | Number of maintained of municipal Public amneties, public open space and parks and cemeteries | Number of reports on maintained of municipal Public amneties, public open space and parks and cemeteries | 4x reports on maintained public areas and cemeteries in the year ending 30 June 2026 | 4x reports on maintained public areas and cemeteries in the year ending 30 June 2026 | 3 250 000 | 4x reports |  |
| CC 2 | Community Services | 5,5,2 | To regularly provide effective services to the Community in order to create clean and safe environment | Compliant landfill site (disposal site) maintained monthly | Number of waste tonnages capped in compliance with Dannhauser LM landfill site licence | Number of reports on waste tonnages capped in compliance with Dannhauser LM landfill site licence | 4x reports of waste capped in the Dannhauser LM landfill site in the year ending 30 June 2026 | 4x reports of waste capped in the Dannhauser LM landfill site in the year ending 30 June 2026 | N/A | 4x reports |  |
| CC 3 | Planning and Economic Development | 5,5,3 | To ensure that the Spatial Development Framework is prepared and aligned with LUMS | Effective Monitoring & Evaluation of Implementation of Spatial Development and Town Planning | Adoption of the reviewed 2025/2026 SDF by council in the year ending 30 June 2025 | Adoption of the reviewed 2025/2026 SDF by council | Adoption of 2025/26 SDF Review by Council by the year ending 30 June 2026. | Date of Adoption of 2025/26 SDF Review by Council by the year ending 30 June 2026. | N/A | Council resolution |  |
| KPA 6: Municipal Financial Viability and Management |  |  |  |  |  |  |  |  |  |  |  |
| Back to Basics: Ensuring sound financial management and accounting |  |  |  |  |  |  |  |  |  |  |  |
| MFV 1 | Budget and Treasury Office | 6,6,1 | To improve expenditure control/Regular monitoring departmental budget to curb irregular expenditure | Departmental budget actually spent within dept budget | % of dept budget actually spent against approved dept budget | % of departmental spent on operational budget against approved budget | 100% spent of the dept annual budget in the year ending 30 June 2026 | 100% of departmental spent on operational budget against approved budget in the year ending 30 June 2026 | NA | 1x expenditure reports |  |
| MFV 2 | Budget and Treasury Office | 6,6,2 | Manage and effect proper by reducing UIFWE | Effect proper control budget and other financial processes which minimise UIFWE | Number of Quarterly reports on irregular, fruitless and unauthorized expenditure | Number of Quarterly reports on irregular, fruitless and unauthorized expenditure | 4 x Quarterly Reports On Irregular, Fruitless and unauthorized Expenditure in the year ending 30 June 2026 | 4 x Quarterly Reports On Irregular, Fruitless and unauthorized Expenditure in the year ending 30 June 2026 | N/A | 4 x Reports SCM reports |  |
| MFV 3 | Budget and Treasury Office | 6,6,3 | Municipality's Budget actually spent on Workplace Skills Plan | Municipality's Budget actually spent on Workplace Skills Plan | % of budget spent on the WSP | % of budget spent on the WSP | 100% spending of the budgeted amount on WSP in the year ending 30 June 2026 | 100% spending of the budgeted amount on WSP in the year ending 30 June 2026 | N/A | 1x report spent on WSP |  |
| MFV 4 | Budget and Treasury Office | 6,6,4 | To effectively manage financial conditional grants | Effective management of grant dependent projects | % of the monthly Grants spent | % of the grants spent | Spend 100% of the Monthly Grants budget in the year ending 30 JUNE 2026 | Spend 100% of the Monthly Grants budget in the year ending 30 JUNE 2026 | NA | 1x Grant spend Report |  |
| MFV 5 | Budget and Treasury Office | 6,6,1 | To improve expenditure control/ regular monitoring departmental budget to curb irregular expenditure | Enhanced municipal budgeting and budget implementation | % of budgeted revenue collected | % of budgeted revenue collected | 100% of budgeted revenue collected by 30 June 2026 | 85% of budgeted revenue collected by 30 June 2026 | N/A | 4x monthly revenue reports |  |
| MFV 6 | Budget and Treasury Office | 6,6,1 |  |  | Number of Supply Chain Management reports prepared and submitted to Mayor & PT | Number of Supply Chain Management reports prepared and submitted to Mayor & PT | 4- Supply Chain Management Quarterly Reports prepared and submitted Mayor & PT by 30 June 2026 | 4- Supply Chain Management Quarterly Reports prepared and submitted Mayor & PT by 30 June 2026 | N/A | The Signed Quarterly reports & the Proof of Submission to the Mayor & PT |  |
| MFV 7 | Budget and Treasury Office | 6,6,1 |  |  | % of Capital budget spent | % of Capital budget spent | 100% Capital budget spent by 30 June 2026 | 100% Capital budget spent by 30 June 2026 | N/A | 1x report spent on capital budget |  |
| MFV 8 | Budget and Treasury Office | 6,6,1 |  |  | Ratio in compliance with MFMA section 54(2)(a) | % Ratio in compliance with MFMA section 54(2)(a) | Maintained outstanding Debtors to revenue ration at less than 0,5 by the end o 30 June 2026 | 50% maintained outstanding Debtors to revenue ration at less than 0,5 by the end of 30 June 2026 | N/A | 4x revenue reports |  |
| MFV 9 | Budget and Treasury Office | 6,6,1 |  |  | Ratio in compliance with MFMA section 54(2)(e) | % Ratio in compliance with MFMA section 54(2)(e) | More than 1 debt coverage ratio maintained at less than 1 for the year ended 30 June 2026 | More than 100% debt coverage ratio maintained at less than 1 for the year ended 30 June 2026 | N/A | 4x revenue reports |  |
| MFV 10 | Budget and Treasury Office | 6,6,1 |  |  | Cash / Cost coverage Ratio | Number Cash / Cost coverage Ratio | More than 1 month coverage ratio maintained for the year ending 30 June 2026 | More than 1 month coverage ratio maintained for the year ending 30 June 2026 | N/A | 4x revenue reports |  |
| MFV 11 | Budget and Treasury Office | 6,6,1 |  |  | Current Ratio | Current Ratio | Statement of financial position to be maintained between 1,5 to 2:1 in the year ending 30 June 2026 | 1x 2024/2025 statement of financial position to be maintained between 1,5 to 2:1 in the year ending 30 June 2026 | N/A | 1x financial statements |  |

|  | Initial Indicator |
| --- | --- |
| I | Revised Indicator |
|  | Initial Target |
|  | Revised Target |